## Goal 1
Goal 1: Meet the educational needs of the local, regional, national, and global communities.
Objectives | Action Items | Focus Questions | Answers | Cross References | Priority
Objective 1: Provide and promote high-quality academic programs that empower students through engagement in relevant, meaningful hands-on learning experiences. | 1. Increase opportunities for research, scholarship, and service for students, faculty, and staff. [Ensure opportunities for research, scholarship, and/or service for students, faculty, and staff.] | How? | Determine a baseline for existing research and scholarship opportunities for students at Minot State. |  | Low Priority
Charge Small Research Grant committee to refocus the rubric to better support research opportunities for students. (Research led by faculty but encourage faculty to engage students in the projects.)
|  | Who? | VPAA and small grants chair
Minot State Committee for Undergraduate Research and Creative Activity
|  | When? | Ongoing
|  | Resources needed: | Invite Small grants committee to explore coordination with Minot State Committee for undergraduate research and creative activity
NDUS Undergraduate Research Council may provide funds and support
Objective 1: Provide and promote high-quality academic programs that empower students through engagement in relevant, meaningful hands-on learning experiences. | 2. Increase student focus on academic activities. [OR Facilitate student engagement in academic activities.] | How? | Reactivate/reimagine the Intellectual Climate Committee (ICC) to include academic events by utilizing student fees to create co-curricular programming that relates to personal student and academic interests | Goal 4 Objective 1 | Low Priority
Seek funding for academic engagement activities (i.e., Red and Green Newspaper) and internships
|  | Who? | SGA in collaboration with the ICC
Career Services
Academic Departments
|  | When? | Ongoing
|  | Resources needed: | A budget for the ICC
Budget for engagement activities and internships
Determine current state of internships on the Minot State campus
Objective 1: Provide and promote high-quality academic programs that empower students through engagement in relevant, meaningful hands-on learning experiences. | 3. Establish responsibility for ongoing regional accreditation requirements. | How? | Create a position who would have primary supervision of HLC and support accreditation for other accredited programs across campus | Goal 1, Objective 1, Item 4 | High priority. In progress. Will hire in summer 2018.
Move to a continuous improvement cycle rather than emergency response
|  | Who? | VPAF/VPAA/Administration find personnel resource
|  | When? | Summer 2018
|  | Resources needed: | Position or reallocate personnel
Objective 1: Provide and promote high-quality academic programs that empower students through engagement in relevant, meaningful hands-on learning experiences. | 4. Develop strategic assessment program for campus. | How? | Redefine/simplify GE requirements (redoing it? Explaining it? Continuous improvement cycle?) {students have to jump through hoops when coming in, just one piece of assessment} |  | High priority
Develop appropriate program assessments.
Develop a campus-wide long-term assessment plan (Includes developing co-curricular assessment plans to set and measure goals related to student learning outcomes)
|  | Who? | Academic Assessment Committee, GE Committee, VPAA, new professional responsible for accreditation, Directors | Goal 1, Objective 1, Item 3
|  | When? | 1-2 years
|  | Resources needed: | Allocated accordingly by VPAA
Objective 1: Provide and promote high-quality academic programs that empower students through engagement in relevant, meaningful hands-on learning experiences. | 5. Prioritize academic programs. | Removed because Objective 2 is in the process to prioritize academic programs
Objective 2: Determine the educational needs of future students and allocate resources accordingly. | 1. Conduct continuous regional needs assessment of future students to determine educational needs. | How? | Analyze existing NDUS data and reports and other sources |  | High Priority Complete first for objective 2.
|  | Who? | Strategic Planning and Budget Council
Director of Institutional Research and VPAA
|  | When? | Start summer 2018
|  | Resources needed: | Access to data and reports from NDUS
Objective 2: Determine the educational needs of future students and allocate resources accordingly. | 2. Develop and discontinue programs based on research outcomes | How? | Create a process to evaluate the relevance and efficiency of existing policies and procedures and adjust accordingly. |  | Medium Priority
Be opportunistic.
|  | Who? | Strategic Planning and Budget Council
Vice presidents and department/division chairs
|  | When? | Ongoing
|  | Resources needed: | Results of needs assessment and institutional data.
Objective 2: Determine the educational needs of future students and allocate resources accordingly. | 3. Reallocate resources to support growth of new and continued programs. | How? | Use a needs-based budget model {start with $0: each budget year, departments start with what you need regardless of what was given in the past; justification of resource allocation. This type of budgeting will make us think about things. What do we need in our areas versus spending just to spend?} |  | Low Priority Under Current Budget Situation
|  | Who? | Strategic Planning and Budget Council
Vice presidents and department/division chairs
|  | When? | Ongoing
|  | Resources needed: | Results of needs assessment
Budget information
Objective 3: Develop and offer curricular and co-curricular programs supporting diverse, multi-generational learners. | 1. Develop programming for diverse age groups. | How? | Note the changing populations and needs of the community. |  | Low Priority
Prior Learning Credit
|  |  | We already have: College for Kids, Professional and Community Education, Certificate programs, COB seminars, Corporate Training, Art - Open studio sessions, CPA review course, Severson Entrepreneurship Academy, Dakota Chamber Music | Goals 5 & 6 - combine forces for summer conferencing, coordinate what is happening
|  | Who? | Do we want to continue with all these offices during different pieces? Should there be an office handling all this?
CEL, COB, SEA, Art Department, Division of Music, Graduate School
|  | When? | Ongoing
|  | Resources needed: | Results of needs assessment
Marketing and advertisement
Faculty and staff commitments
Objective 3: Develop and offer curricular and co-curricular programs supporting diverse, multi-generational learners. | 2. Create innovative program offerings based on mode, modularity, and scheduling. | How? | Find and incentivize innovative faculty who are willing to try new approaches |  | High Priority
Determine barriers to innovation
Identify areas for experimentation
Provide opportunities for faculty to keep up-to-date on available teaching resources via faculty training and professional development for effective pedagogy.
|  | Who? | CEL, departments, and VPAA
|  | When? | Ongoing
|  | Resources needed: | Incentive funds
Technology to support new offerings and approaches
Training and professional development
Partners

## Goal 2
Goal 2: Recruit, retain, and value well-qualified students, faculty, and staff.
Objectives | Action Items | Sections | Focus Questions | Answers | Cross References | Priority
Objective 1: Support and increase student enrollment and retention. | 1. Offer multi-year scholarship packages to recruit and retain quality students. | Freshman plan |  | In progress; See automatic 4-year awards at http://www.minotstateu.edu/enroll/scholarships.shtml |  | High Priority - In progress
Objective 1: Support and increase student enrollment and retention. | 1. Offer multi-year scholarship packages to recruit and retain quality students. | Create a Transfer Scholarship Plan | How? | Need affordable plan |  | High Priority
|  |  | Who? | VPAF, Financial Aid, Enrollment Services, Advancement
|  |  | When? | 1-2 years
|  |  | Resources needed: | More endowed resources in general scholarships for more total dollars
Objective 1: Support and increase student enrollment and retention. | 1. Offer multi-year scholarship packages to recruit and retain quality students. | "Grants" from the foundation | How? | Awarded to students (not based on academic performance) but must be paid back if they do not meet satisfactory progress |  | Low Priority
|  |  | Who? | Advancement
|  |  | When? | ??
|  |  | Resources needed: | Data for juniors and seniors who receive aid (or do not receive aid)
Objective 1: Support and increase student enrollment and retention. | 2. Prioritize resources for student on-campus work, internships, and research. | One-stop shop including career services for campus work and internships | How? | Consolidate student academic support services: tutoring, disability student services, writing center, peer mentors, career services, etc. | Goals 1, 3, 5, 6 See Goal 3, Objective 2, Action Item 3 | Medium Priority - too much in this one action item.
|  |  | Who? | Ad Hoc Committee and Assistant VPAA, VPAA
|  |  | When? | Summer 2018
|  |  | Resources needed: | Dining services plan (needs to precede this and is starting 2017-2018) to determine possible space allocation | Goal 2, Objective 1, Item 4
Retrieve notes from the Ad Hoc Committee on Interdisciplinary Studies, Academic Student Services, and Engagement
Explore how internships work within each department/college - perhaps need a point-person for each college
|  |  |  | Consider 21st Century Workforce resources | Goal 3, Objective 2, Item 1, Section 2 Goal 4, Objective 1, Item 1, Section 4 Goal 5, Objective 3, Item 1, Section 1 Goal 6, Objective 1, Item 2
Objective 1: Support and increase student enrollment and retention. | 2. Prioritize resources for student on-campus work, internships, and research. | Student Research | How? | Dependent upon academic department budgets and curricula |  | Low Priority
|  |  | Who? | Academic departments and NDUS Undergraduate Research Council
|  |  | When? | Dependent upon departments and NDUS/legislative funding
|  |  | Resources needed: | Curriculum changes, faculty load policy for research, funding would help
Objective 1: Support and increase student enrollment and retention. | 3. Enhance and innovate recruitment, retention, promotion, and branding strategies. | Minot State has a silo structure that needs to change to enhance and innovate recruitment, retention, promotion, and branding strategies |  | How? Reorganization Who? President's Staff When? 2018-2020 Resources needed. Attention to detail, positive energy |  | Medium Priority
Objective 1: Support and increase student enrollment and retention. | 3. Enhance and innovate recruitment, retention, promotion, and branding strategies. | Enrollment Management must be integrated as an on-going responsibility of all Minot State departments and all employees |  | How? Ensure everything we do is student-friendly and promote a student-focused culture. Who? All Minot State departments and all employees When? 2018-2020 Resources needed. Attention to detail, positive energy | Goal 2, Objective 1, Items 4,5 | Medium Priority
Objective 1: Support and increase student enrollment and retention. | 3. Enhance and innovate recruitment, retention, promotion, and branding strategies. | Four-year academic plans available/ deployed for most academic programs | How? | Make available on department webpages and as an accurate listing in the degree audit in Campus Connection (or catalog or other online location) |  | High Priority
|  |  | Who? | Academic departments, VPAA
|  |  | When? | By Fall 2018
|  |  | Resources needed: | Find the four-year plans submitted previously, determine a template, and have departments update them using template
Keep plans up-to-date each year; create an annual deadline on the academic affairs calendar
Put in a central online location and have departments link there
Objective 1: Support and increase student enrollment and retention. | 3. Enhance and innovate recruitment, retention, promotion, and branding strategies. | Branding Strategies | How? | Branding consultant |  | High Priority - In progress
|  |  | Who? | Flint from Fargo
|  |  | When? | In-progress
|  |  | Resources needed: | Time and money; feedback from various groups on campus
Objective 1: Support and increase student enrollment and retention. | 4. Expand and enhance student academic support services. | One-Stop Shop for Academic Support Services |  |  | Goal 2, Objective 1, Item 2 See Goal 3, Objective 2, Action Item 3 | Medium to High Priority - In progress (Medium - advising)
Objective 1: Support and increase student enrollment and retention. | 4. Expand and enhance student academic support services. | Modify Advising Structure? |  |  | Goal 2, Objective 1, Items 3,5
Objective 1: Support and increase student enrollment and retention. | 5. Revise and implement strategic enrollment management plan. | Strategic Enrollment Management (SEM) plan (for all campus) | How? | 1. Develop a vision statement that SEM is the responsibility of all departments | Goal 2, Objective 1, Items 3,4 Goal 2, Objective 2, Item 2 | Medium Priority
2. SEM committee with a broad cross section of campus (especially those faculty who report back to Faculty Senate) - Marketing Director and Enrollment Services included; Committee Chair = executive level or respected faculty member
3. Establish in all employee expectations that students are central to Minot State's mission and should be the primary focus of all University actions
|  |  |  | 4. Review internal processes to remove barriers | Goal 2, Objective 1, Item 5, Section 3
|  |  | Who? | All departments
|  |  | When? | As soon as possible
|  |  | Resources needed: | Reorganization of university; Visibility for everyone to find; Bring in accountability to this plan (i.e., through evaluations)
Objective 1: Support and increase student enrollment and retention. | 5. Revise and implement strategic enrollment management plan. | Operational Plan (for Enrollment Services) | How? | Dependent upon what is in the SEM plan |  | Medium Priority
|  |  | Who? | Enrollment Services
|  |  | When? | As soon as possible
|  |  | Resources needed: | More staff
Objective 1: Support and increase student enrollment and retention. | 5. Revise and implement strategic enrollment management plan. | Remove barriers to enrollment | How? | Study inquiry-applicant processes to coordinate efforts across campus |  | High Priority
Simplify enrollment - challenge all departments to ensure all processes and procedures are student-focused (Address student holds; Simplify new student enrollment; Recruit Back Program)
Study competitors regarding financial aid strategies and program promotions
|  |  |  | Develop an active presence at two-year colleges (2 + 2 programs for appropriate programs at BSC, WSC, and DCB; Marketing of programs at two-year institutions) | Goal 5, Objective 1, Item 4, Section 1
Fix internal processes for new transfer students
Replace the net price calculator and gear it toward recruitment
Track applicants who do not enroll for purposes of future financial aid restructuring
Exit counseling for non-returning current students
Ensure high quality academic advising
Assure class availability for non-traditional students and lifetime learners (evening and summer course availability)
Ensure proper four-year course sequencing to promote four-year graduation guarantee for most programs
|  |  | Who? | Multiple areas depending on item above
|  |  | When? | As soon as possible
|  |  | Resources needed: | Data, time, procedural changes, program adjustments
Objective 1: Support and increase student enrollment and retention. | 5. Revise and implement strategic enrollment management plan. | Allow CEL autonomy for program flexibility | How? | Encourage CEL and departments to hire faculty and deliver coursework in response to community demand |  | Medium Priority
|  |  | Who? | CEL and departments
|  |  | When? | As soon as possible
Resources needed:
Objective 2: Support and value commitment to teaching, scholarship, and service. | 1. Expand "grow your own" program. |  | How? | Start by evaluating current practices by gathering faculty and staff input via survey, followed by open forum to discuss results |  | Medium Priority
Look into sabbatical leave program for non-tenured/promoted professors and/or staff
|  |  | Who? | Faculty and Staff Senate, President's Staff, VPAA
|  |  | When? | 2019
|  |  | Resources needed: | This will require reallocation of funds (current: advanced study grants) and resources.
Community encouragement to complete an advanced degree.
What incentives are available for staff to continue their educational journey (succession programs)?
Look into requirement of commitment to Minot State after completing the program
How do we keep current students at Minot State as employees after graduating?
Objective 2: Support and value commitment to teaching, scholarship, and service. | 2. Continue to emphasize role of faculty in shared governance. |  | How? | Expand faculty role in strategic enrollment planning | Goal 2, Objective 1, Item 5, Section 1 | Low Priority
|  |  |  | Increased responsibility of the salary and budget committee (faculty senate subcommittee) | Goal 2, Objective 2, Item 4
Academic Visioning group (VPAA tasked from Faculty Senate)
|  |  | Who? | Faculty Senate, Chairs
|  |  | When? | In progress
|  |  | Resources needed: | Create a culture of participation in committees at Minot State
Objective 2: Support and value commitment to teaching, scholarship, and service. | 3. Reevaluate the role of full-time vs. part-time faculty in stabilizing academic program delivery and program quality. |  | How? | Determine the current status and establish an acceptable range of each type of faculty member |  | Low Priority
Define tenure track, non-tenure track/special contract, and adjunct faculty
|  |  | Who? | Chairs
|  |  | When? | By 2019
|  |  | Resources needed: | Use HLC standards to ensure we have the credentialed faculty requirements and the right mix of full-time and part-time
Objective 2: Support and value commitment to teaching, scholarship, and service. | 4. Develop and implement institutional compensation strategy. Combine with Goal 3, Obj. 5, Action Item 1 - 1. Analyze salary equity and address the findings. |  | How? | Increased responsibility of the salary and budget committee to look at gender equity, discipline equity, and position equity | Goal 2, Objective 2, Item 2 | High Priority - In progress
|  |  | Who? | Faculty Senate Salary and Budget Committee, HR Director (on the committee), potential Staff Senate Salary and Budget Committee
|  |  | When? | In progress
|  |  | Resources needed: | CUPA data, Minot State equity survey results
Objective 3: Offer professional development support to encourage commitment to the mission and vision. | 1. Support staff professional growth opportunities. |  | How? | Departments should prioritize as needed to make it known in future budget requests. |  | Medium Priority
|  |  | Who? | Staff Senate, potentially the Staff Senate Salary and Budget Committee, HR
|  |  | When? | As soon as possible
|  |  | Resources needed: | Utilize on-campus expertise or bring in on-campus opportunities to expand professional development
Ensure budget dollars available for professional development opportunities
Objective 3: Offer professional development support to encourage commitment to the mission and vision. | 2. Establish regular cycle of academic technology and policy training for campus. |  | How? | Academic technology as budget allows |  | Medium Priority
Policy training for IT procedures
Mini sessions during faculty convocation
|  |  | Who? | VPAF, ITC
|  |  | When? | In progress [policy training/training on available technology is a critical need]
|  |  | Resources needed: | Consider including policy training for Business Office, Facilities, and HR departments | Goal 2, Objective 3, Item 4
Objective 3: Offer professional development support to encourage commitment to the mission and vision. | 3. Expand the availability of and participation in faculty development efforts focused on engaged pedagogy for today's students. |  | How? | Departments should prioritize and request additional funding when needed |  | High Priority
Bring experts to campus for development opportunities or send faculty to PD opportunities with the expectation that they implement and share what they learned
Reinvigorate a PIL-like program and regular dialogues about teaching
|  |  | Who? | Chairs and VPAA
|  |  | When? | As soon as possible - Summer 2018
|  |  | Resources needed: | Subject to availability of funds
Objective 3: Offer professional development support to encourage commitment to the mission and vision. | 4. Review and update campus policies. |  | How? | Constantly ongoing in conjunction with NDUS policy development |  | Medium Priority - In progress
Include training on policy and procedure
|  |  |  | Provide improved training for employees and communication to employees are critical | Goal 2, Objective 3, Item 2
|  |  | Who? | Vice Presidents and respective departments
|  |  | When? | In progress
|  |  | Resources needed: | Include multiple modalities of training options
Faculty and Staff Senates should convey information on policies in question
Objective 3: Offer professional development support to encourage commitment to the mission and vision. | 5. Commit to performance metrics, accountability, and use of data in the evaluation of employees and programs. |  | How? | Ensure consistency of employee evaluations between departments by revising staff evaluation forms |  | High Priority`
Determine consistency of performance metrics where appropriate
|  |  | Who? | VPAA and chairs (for faculty); HR (for staff), President
|  |  | When? | As soon as possible
|  |  | Resources needed: | Investigate merit-based salary increases

## Goal 3
Goal 3: Create an institutional environment that supports student, faculty, and staff success.
Objectives | Action Items | Sections | Focus Questions | Answers | Cross References | Priority
Objective 1: Provide support and institutional resources to accommodate all learners. | 1. Enhance the range of student academic and counseling support services, and widen access to them for all students | Academic Support Services | How? | Investigate current services, determining gaps in subject areas and areas where needs may not have been met |  | High Priority - See in other goals
Determine where/how all academics services are housed and accommodated
Create proposal to adjust current services based on data
Adjust resources to support new plan
|  |  | Who? | SPBC sub-committee
SPBC sub-committee
Academic Support Service areas (Disability Student Support Services, CETL, POWER, Career Services, International Student Services)
President, VPAA, VPFA
|  |  | When? | Spring 2019
|  |  | Resources needed: | Current services; location; services offered
Usage data for each service - determine what is being used and the effectiveness of the service
Objective 1: Provide support and institutional resources to accommodate all learners. | 1. Enhance the range of student academic and counseling support services, and widen access to them for all students.. (Combined with Goal 4, Obj. 3, Action Item 2 - Improve access to mental health services on campus) | Counseling Support Services | How? | Review findings from past surveys, continue to investigate current services, determining areas with high demand, needs not met, expertise available vs. needs |  | High Priority
Ensure all (current and new) full-time and part-time staff qualifications and licensures
Review current agreements and collaborations with local health agencies
Create proposal to adjust current services based on data
Secure agreements with local health agencies as needed
Provide plan for supporting student access to needed services
Adjust resources to support new plan
|  |  | Who? | Wellness Center Director
Student Development and Health Services Director(s)
|  |  | When? | Fall 2018
|  |  | Resources needed: | Current services offered
Survey of clients to determine needs met/not met
Usage data
Credentials of current staff
Objective 1: Provide support and institutional resources to accommodate all learners. | 2. Ensure the library can meet the academic needs of the campus. |  | How? | Survey faculty, staff, and students to determine needs; request areas prioritize their needs |  | Medium Priority
Review and establish price points for requests
Establish short-term and long-term plans for addressing campus needs based on data
|  |  | Who? | Library Staff
|  |  | When? | Fall 2019
|  |  | Resources needed: | Survey of actual library usage (data and use) and needs
Student usage data
Objective 1: Provide support and institutional resources to accommodate all learners. | 3. Develop and implement a plan to update all classroom space and technology on a rotating basis. |  | How? | a. Conduct physical inspection of all classroom technology and space, noting current needs |  | Medium Priority
b. Survey faculty regarding their classroom instructional needs
c. Create technology templates for different types of classrooms
d. Create update schedules for each type of classroom
e. Determine schedule of physical updates to classrooms, with priority to those needing least expensive cosmetic updates due to budget limitations
f. Establish a campaign to freshen up the campus, inviting student groups and classes to volunteer for classroom updates (painting, for example). Could even have a competition
g. Determine schedule of physical updates to classrooms needing minor to major renovation, including cost estimates
|  |  | Who? | SPBC sub-committee (steps a-b)
IT Central (steps c-d)
Facilities, VPAA, VPFA (step e)
VPAA/CETL/SGA (step f)
Facilities, VPAA, VPFA (step g)
|  |  | When? | Fall 2019
|  |  | Resources needed: | Inspection of classrooms, inventory of current technology in classrooms; usage, needs to meet usage
Survey of faculty classroom needs
Survey students for classroom space and technology needs
Facilities (?) list of classroom physical updates (paint, furnishings, carpet, etc.)
|  |  |  | Budget allocations | "See Goal Two, action item"
Objective 2: Improve student retention and graduation rates. | 1. Enrich academic advising, mentoring, and new programming for students. | Advising and Mentoring | How? | Develop and implement a plan to shift colleges to centralized academic advising |  | High Priority
Shift faculty to career mentoring role
Expand opportunities for peer mentoring into lower level courses other than UNIV
|  |  | Who? | VPAA, chairs in CEHS and CAS
Chairs, CEHS and CAS
Chairs, VPAA
|  |  | When? | Fall 2018-Spring 2019
|  |  | Resources needed: | Faculty buy in
Staff (academic advising)
Additional peer mentoring staff/reallocation of funds for peer mentors
Feedback on current peer mentor effectiveness
Objective 2: Improve student retention and graduation rates. | 1. Enrich academic advising, mentoring, and new programming for students. | New programming for [undergraduate?] students | How? | Include student led sessions in Be in the Know |  | Low Priority
Expand University Communication to students to include Instagram, Snapchat, and/or text notifications
|  |  |  | 21st Century Workforce | Goal 2, Objective 1, Item 2, Section 1 Goal 4, Objective 1, Item 1, Section 4 Goal 5, Objective 3, Item 1, Section 1 Goal 6, Objective 1, Item 2
Address student retention in years 2 and 3
NSO, PTO, Welcome Weekend (New Student Convocation): Fall intake; Spring intake; Transfer students; Online students/distance students
|  |  | Who? | SGA, Marketing, University Communications, CETL, Career Services, Retention Committee
|  |  | When? | Fall 2018
|  |  | Resources needed: | Oversight for social media
Review data pertaining persistence rates: Admit type; Enrollment status; Many variables can affect retention, look for patterns to help determine strategies
Objective 2: Improve student retention and graduation rates. | 1. Enrich academic advising, mentoring, and new programming for students. | Consider programming for graduate students? | How? | Orientation for International graduate students | *Add graduate assistantships to retention and recruitment for graduate students (Goal 2) | Low Priority
|  |  | Who? | Graduate School
International Office
|  |  | When? | Fall 2018
|  |  | Resources needed: | Time
Objective 2: Improve student retention and graduation rates. | 2. Enhance career services and increase meaningful experiential opportunities. |  | How? | Examine role of Career Services at institutions similar to Minot State | Meaningful experiential opportunities also discussed in Goal 6, not covered in Goal 3 | Medium Priority
Create a plan to update MSU career services based on other institutions' offerings
Consider relocating Career Services to the CETL office to provide better transition for students
|  |  | Who? | Career Services
Career Services/CETL
VPAA, VPSA, CETL, Career Services
|  |  | When? | Fall 2018
|  |  | Resources needed: | Survey or web observation of CS at other institutions
Objective 2: Improve student retention and graduation rates. | 3. Streamline and centralize student success services. |  | How? | a. Define student success services; inventory current services and offerings | Academic Support Services consolidation is also addressed in Goal 2 | High Priority
b. Determine current and needed expertise for student success services
c. Examine current job descriptions; update and combine where possible
d. Establish centralized location for Student Success Services, and relocate all services to one building/area (one-stop shop[s])
Student Support Services: Enrollment Services, Registrar's Office, Financial Aid, Business Office
Student Health Center, Wellness Center, Veterans Center, Lutheran Campus Ministries, Multicultural Center, International Programs, Native American Center, Student Activities (M Life), Student Government Association, Residence Life
CETL (Peer Mentors, New Student programming and first year experiences)
Academic Support Services: Advising, tutoring, Career Services/Student Success Center, POWER, Writing Center, Disability Student Services, Testing Center
|  |  | Who? | SPBC sub-committee (Steps a & b)
VPAA, VPSA, area leaders (Step c)
President's Staff, area leaders, facilities (Step d)
|  |  | When? | Fall 2018
|  |  | Resources needed: | Current services offered
Survey students for service needs
Compile data of student usage of services
Review final report of ad-hoc committee on consolidating academic support services
Job descriptions of student services personnel
Floor plan of possible areas for relocation - look for minimal renovation needs
Review best practices
Objective 2: Improve student retention and graduation rates. | 4. By 2023 attain graduation rate of 50% and retention rate of 80%. |  | How? | Establish volunteer committee of faculty and staff to activate during registration periods and contact students to encourage and assist in registration - start fall 2018 | Some additional retention steps addressed in Goal 2 | High Priority
Create program for stopped-out students: Provide peer mentors; Provide incentives for return to complete; Establish academic success plan. Start Spring 2019
Create cohort options, such as living-learning communities, for campus and off-campus students. Ongoing
Offer concentrations in condensed sessions: Summer sessions, including May-mesters, Night classes - 8 week, two semesters. Ongoing
Complete comprehensive online programming. Start spring 2019 (gen ed)
|  |  |  | Review and revise process for recruit back strategies | Same as Stopped Out.
|  |  |  | Identify retention strategies specific for Minot State | Make Minot and Minot State as a destination; Increase engagement activities and make sure departments on campus provide access when needed - Potentially goal 4 (yes!)
|  |  |  | Identify and implement effective pedagogy to retain students. CETL should do. | Where does Prior Learning Credit for new students fit in the strategic plan?
Implement Financial Aid counseling, financial planning for students. Ongoing
|  |  | Who? | VPAA, chairs
VPAA, chairs, Financial Aid, Registrar, Advisor(s)
VPAA, VPSA, Residence Life, CETL, chairs
Chairs
Retention Committee
|  |  | When? | Fall 2023
|  |  | Resources needed: | Faculty and staff volunteers for reaching out to students
Financial Aid resources for incentives for recruitment
Funding for concentration offerings in condensed sessions
Departments should review PAR data
Best practices and literature for retention practices
Financial aid staff and resources?
Objective 3: Design, implement, and support technology resources to ensure security of data and the physical plant. | 1. Cooperate with NDUS to increase campus data security and integrity. |  | How? | Continue and increase current practices aligned with NDUS policy: Dual authentication; IT phishing and scam messages |  | Low Priority
Provide Be in the Know sessions for campus information - current policies at state and local level, examples of issues, what to do, etc.
Provide monthly or semi-monthly e-flyer on data security and integrity issues
|  |  | Who? | IT Central
Marketing, IT Central
Marketing, IT Central, BIT or CSCI Faculty
|  |  | When? | Fall 2018
Resources needed:
Objective 3: Design, implement, and support technology resources to ensure security of data and the physical plant. | 2. Increase student access to study resources. |  | How? | a. Investigate current study area access hours and after hour building policies and practices |  | Medium Priority
b. Survey student needs for study access
c. Using data, recommend revisions to after hour building access policies and practices
d. Approve updated access policies and practices
e. Install card access to all buildings and rooms for students' after-hour access (determine status of cards first)
|  |  | Who? | SPBC sub-committee, facilities (steps a-c)
Buildings facilities, VPFA, security
VPFA, facilities
|  |  | When? | Spring 2020
|  |  | Resources needed: | Current hours, policies for all study spaces
Data on usage of current study spaces
Survey of student study area access needs
Objective 3: Design, implement, and support technology resources to ensure security of data and the physical plant. | 3. Expand use of existing technologies to reduce student fees and multiple logins. | Committee recommends elimination of this Action Item. Item was included as a response to one student's concern about having logins for both Blackboard and a course-specific program. NDUS uses one login/password system now.
Objective 3: Design, implement, and support technology resources to ensure security of data and the physical plant. | 4. Automate common workflow processes to increase efficiency and reduce paper processes. |  | How? | Determine current paper processes |  | Medium Priority
Establish revision plans
Secure necessary software for new processes (example - VPAA needs software to automate Faculty Load Reports)
Assess success of conversion to electronic processes
|  |  | Who? | SPBC subcommittee, units
Units
VPAF, units
Units
|  |  | When? | Spring 2020
|  |  | Resources needed: | Survey of campus units to determine paper processes; data regarding usage of each paper process to determine feasibility of automation
Objective 4: Empower students, faculty, and staff to seek and secure external funding. | 1. Reinstate the Office of Sponsored Programs. |  | How? | Investigate interest in and potential for SP office |  | Medium Priority
|  |  |  | If supported, create part-time position for SP director - 50%? | Goal 3, Objective 4, Item 2
|  |  | Who? | SPBC or VPAA
President's staff
|  |  | When? | Fall 2019
|  |  | Resources needed: | Survey of campus to determine interest, potential services, use
Objective 4: Empower students, faculty, and staff to seek and secure external funding. | 2. Implement incentive program for faculty/staff/students securing external funding. |  | How? | Pending Office | Based on Action Item 1, assign this task to the SP director | ??
Who?
|  |  | When? | Spring 2020
Resources needed:
Objective 4: Empower students, faculty, and staff to seek and secure external funding. | 3. Increase public awareness of current research and scholarship. |  | How? | Create online repository for faculty/staff/students to post success; University Communication (UC) can access this information for stories |  | Medium Priority ??
Suggest similar process be implemented at state level
|  |  | Who? | University Communications
|  |  | When? | Fall 2018
Resources needed:
Objective 4: Empower students, faculty, and staff to seek and secure external funding. | 4. Establish MSU Research Center of Excellence. |  | How? | Pending Center | Committee recommends tabling until Action Item 1 is in place and/or funding situation is stable
Who?
When?
Resources needed:
Objective 5: Expand an environment that values and supports diversity. | 1. Analyze salary equity and address the findings. Combine with Goal 2, Obj. 2, Action Item 4 |  | How? | a. Analyze salary equity on campus, state, regional, and national basis |  | High Priority
b. Share findings in campus forum and through written reports
c. Assign sub-committee to research solutions to inequities if they exist
d. Share solutions and recommendations
e. Assess recommendations based on current and future budget projections. Adjust.
f. Create plan to implement recommendations
|  |  | Who? | SPBC sub-committee (steps a-d)
President's staff
SPB
|  |  | When? | Fall 2019 (some activities are ongoing)
|  |  | Resources needed: | Access to salary data
Objective 5: Expand an environment that values and supports diversity. | 2. Extend diversity and inclusion awareness for campus community. |  | How? | a. Inventory current diversity committees/councils/groups and their activities (Done) |  | Medium Priority
b. Create umbrella organization - Diversity Council - to oversee all diversity groups identified in a. (Done. Mandate all diversity under Diversity Council.)
c. Reinstate the Campus Climate Survey (analyze and share information; create action plan based on results) (Lisa Dooley Title IX survey being done.)
d. Align MSU activities with state initiatives as advertised on the soon-to-be developed state website of diversity events (ongoing)
|  |  | Who? | Diversity Council
|  |  | When? | Pending information
|  |  | Resources needed: | Current groups and their services and activities; Student involvement data
Objective 5: Expand an environment that values and supports diversity. | 3. Expand curricular and co-curricular diversity initiatives. |  | How? | Increase involvement at campus diversity events (HOW?) |  | Medium Priority
Incorporate diversity awareness into UNIV (assignments to attend event or mini-projects) (ongoing)
Request all units have an annual diversity goal in their planning
|  |  | Who? | UNIV instructors, CETL
President's staff, unit directors, chairs, Retention Committee, FYE subcommittee
|  |  | When? | Spring 2020
|  |  | Resources needed: | Data from current events
Objective 5: Expand an environment that values and supports diversity. | 4. Strengthen policies and options for inclusive housing and residence life programming. |  | How? | a. Investigate and discuss options for increasing inclusiveness and acceptance of inclusiveness in residence halls |  | High Priority
b. Evaluate and update policies to align with inclusiveness practices (ongoing)
c. Encourage residence life programming to collaborate with curricular and co-curricular units' activities and events
|  |  | Who? | Residence Hall director, Diversity Council, Title IX (steps a-b)
Residence Hall activities directors, units and chairs
|  |  | When? | Fall 2018
|  |  | Resources needed: | Policies from other campuses

## Goal 4
Goal 4: Promote and support the well-being of students, faculty, and staff, enabling them to address challenges across generations.
Objectives | Action Items | Sections | Focus Questions | Answers | Cross References | Priority
Objective 1: Provide the necessary resources to enrich the campus experience and enhance campus life. | 1. Promote campus resources to MSU and Minot communities. |  | How? | Create professional development activities for management and employees to acquire strategies to respond to Minot State's desired campus culture - inclusiveness; each individual is a part of the Minot State family; make each person feel like they belong, strong advising, etc. |  | Medium Priority
|  |  | Who? | President's Staff, HR
|  |  | When? | Within the next nine months
|  |  | Resources needed: | $$ for training
Objective 1: Provide the necessary resources to enrich the campus experience and enhance campus life. | 1. Improve campus life for students, faculty and staff in the Beaver Dam. |  | How? | Evaluate current use of the Beaver Dam to determine how additional activities and food service can be enhanced to an already hearty list of activities to enrich the campus experience for our students, faculty and staff. Expand the hours, offer various food choices, update furniture, and overall layout of the space. |  | Medium Priority combined 1.4 with this one - eliminate 1.4 New content in blue boxes
We could consider organizing family nights in the Dam when students are on breaks and/or during the semester - e.g. movie night, game night, activities for students and their families, etc.
|  |  | Who? | SGA, Student Activities Committees, Staff Senate, Faculty Senate, VPSA
|  |  | When? | Evaluate by May 10, 2018?
Programming to start Fall 2018 school year
|  |  | Resources needed: | Late night programming costs; New video equipment, new furniture, remodeling costs
Objective 1: Provide the necessary resources to enrich the campus experience and enhance campus life. | 1. Promote campus resources to MSU and Minot communities. |  | How? | Offer events to faculty, staff, and students that feature our own faculty and students showcasing their research projects, sharing their expertise, communicating student experiences (study abroad, conference highlights, student teaching wellness in foreign countries, etc.) aimed at the learning and development of our students |  | High Priority
Who?
|  |  | When? | September 2018
Resources needed:
Objective 1: Provide the necessary resources to enrich the campus experience and enhance campus life. | 1. Promote campus resources to MSU and Minot communities. |  | How? | Work specifically with the Chamber, local and regional businesses, Downtown Business Association, school systems, etc. to bring their experts to the campus to add value to our student learning. One idea is a trivia contest between the City of Minot, school system teachers, and our own students. |  | Medium Priority
Who?
|  |  | When? | 2019
|  |  | Resources needed: | Use the 21st Century Workforce Program participants as a base for this activity | Goal 2, Objective 1, Item 2, Section 1 Goal 3, Objective 2, Item 1, Section 2 Goal 5, Objective 3, Item 1, Section 1 Goal 6, Objective 1, Item 2
Objective 1: Provide the necessary resources to enrich the campus experience and enhance campus life. | 1. Promote campus resources to MSU and Minot communities. |  | How? | What do we do for online students that live within 20 miles of campus? |  | Medium Priority
Who?
When?
Resources needed:
Objective 1: Provide the necessary resources to enrich the campus experience and enhance campus life. | 1. Promote campus resources to MSU and Minot communities. |  | How? | Club meeting venue like the Westlie Room - Lower level of Student Center is a possibility - Make the Student Center more student friendly |  | Medium Priority
Who?
When?
Resources needed:
Objective 1: Provide the necessary resources to enrich the campus experience and enhance campus life. | 2. Bolster intramural and club programs. |  | How? | Assess current status of programs to determine future strategies. Examples: Create new campus, off-campus and online club programs for students; Investigate opportunities to have intramural competitions within the NDUS schools; Develop new programing utilizing the air supported dome | Goal 4, Objective 3, Item 1, Section 5 Goal 5, Objective 3, Item 2, Section 3 | Low Priority
|  |  | Who? | Music, Student life, CAS, CEHS, COB, Wellness Center, Athletics, faculty and staff advisors
|  |  | When? | December 2018
|  |  | Resources needed: | SGA and Student Activities
Objective 1: Provide the necessary resources to enrich the campus experience and enhance campus life. | 3. Enhance outdoor activities and beautification of our campus. |  | How? | Review, update, and prioritize the master landscaping plan to begin implementation of unfinished elements and continue with year-round campus beautification needs |  | Low Priority
|  |  | Who? | President's Staff & Campus Beautification Committee
|  |  | When? | January 2018
|  |  | Resources needed: | Budget for implementation
Objective 1: Provide the necessary resources to enrich the campus experience and enhance campus life. | 3. Enhance outdoor activities and beautification of our campus. |  | How? | Enhance campus activities by adding casual seating elements to the grounds |  | Low Priority
|  |  | Who? | VPAF, SGA, Faculty and Staff Senates
|  |  | When? | Summer 2019
|  |  | Resources needed: | Budget for purchases
Objective 1: Provide the necessary resources to enrich the campus experience and enhance campus life. | 4. Expand the use of the Beaver Dam. |  | How? | Expand the use/aesthetics of the Beaver Dam including the food/drink area. |  | delete
Expand the hours, offer various food choices, update furniture, and possible remove the Cheers bar.
|  |  | Who? | SGA, VPSA, Wellness Center staff
|  |  | When? | Underway
|  |  | Resources needed: | SGA, Sodexo, Student Activities Committee, Wellness Center
Objective 2: Promote campus opportunities that encourage balance in academics, work, and social life. | 1. Integrate the 8 Dimensions of Wellness into campus life. |  | How? | Via FYEs, Residence Life, new faculty and staff orientations, and the senates, promote the wellness policy to encourage a culture of well-being via the 8 Dimensions of Wellness for students, staff, and faculty
|  |  | Who? | Wellness Center, Faculty and Staff Senates, Student Activities Committee, Residence Life, CETL
|  |  | When? | July 1, 2018
|  |  | Resources needed: | Minimal
Objective 2: Promote campus opportunities that encourage balance in academics, work, and social life. | 1. Integrate the 8 Dimensions of Wellness into campus life. |  | How? | Review the wellness policy in the employee handbook to ensure fairness
|  |  | Who? | President's Staff and Staff Senate
|  |  | When? | Immediately
Resources needed:
Objective 2: Promote campus opportunities that encourage balance in academics, work, and social life. | 2. Expand the use of the Wellness Center. |  | How? | Review and determine/update policies, including hours, to allow students and non-Wellness Center members/entities to use/rent the Wellness Center. This includes sponsored memberships that students, faculty, and staff could purchase by the day or month for another individual. |  | Low to Medium Priority
|  |  | Who? | VPFA, Wellness Center staff
|  |  | When? | May 2018
|  |  | Resources needed: | The goal would be to create a cash-flow stream and expanded hours, if needed.
Objective 2: Promote campus opportunities that encourage balance in academics, work, and social life. | 2. Expand the use of the Wellness Center. |  | How? | Review the Wellness Center hours, especially on weekends and evenings |  | DELETE - combined with above
|  |  | Who? | Students, faculty, and staff
|  |  | When? | By May 2018
Resources needed:
Objective 2: Promote campus opportunities that encourage balance in academics, work, and social life. | 3. Develop living and learning communities that offer support, co-curricular involvement, and inclusion. |  | How? | Strengthen the two communities currently being offered | "Also in Goal 3: Objective 5" | Medium Priority
|  |  | Who? | Residence Life, CETL, Wellness Center
|  |  | When? | In progress
|  |  | Resources needed: | $0.00
Objective 3: Meet the health, nutrition, physical environment, and safety needs of the campus community. | 1. Evaluate facility use and condition, and strategically plan for the future. |  | How? | Evaluate Sodexo's food service plans |  | High Priority - Done
|  |  | Who? | VPSA, SGA, and President's Staff
|  |  | When? | In progress
Resources needed:
Objective 3: Meet the health, nutrition, physical environment, and safety needs of the campus community. | 1. Evaluate facility use and condition, and strategically plan for the future. |  | How? | Renovate Cook, Dakota, McCulloch, Pioneer, Lura and Campus Heights |  | High Priority
|  |  | Who? | President's Staff and Residence Life, MSU Foundation
|  |  | When? | Prioritize needs and begin immediately
|  |  | Resources needed: | $$$$$
Objective 3: Meet the health, nutrition, physical environment, and safety needs of the campus community. | 1. Evaluate facility use and condition, and strategically plan for the future. |  | How? | Hire, train, and hold accountable custodial staff/services to adequately maintain the campus infrastructure. Hire/outsource custodial services to provide exceptionally clean and well-kept spaces for our internal and external constituents. |  | On-going
|  |  | Who? | VPFA & Facilities
|  |  | When? | Immediately
|  |  | Resources needed: | Reallocate current budgets/dedicate new funds
Objective 3: Meet the health, nutrition, physical environment, and safety needs of the campus community. | 1. Evaluate facility use and condition, and strategically plan for the future. |  | How? | Update seating in the Dome |  | In progress
|  |  | Who? | Athletics and VPA
|  |  | When? | In progress
|  |  | Resources needed: | Private funding
Objective 3: Meet the health, nutrition, physical environment, and safety needs of the campus community. | 1. Evaluate facility use and condition, and strategically plan for the future. |  | How? | Fully use the potential of the air-supported dome; Determine future options outside of athletics that the air-supported dome could be used to bring more community members to the facility | Goal 4, Objective 1, Item 2 Goal 5, Objective 3, Item 2, Section 3 | High Priority - In progress
|  |  | Who? | Athletics and the campus
|  |  | When? | In progress
|  |  | Resources needed: | ??
Objective 3: Meet the health, nutrition, physical environment, and safety needs of the campus community. | 2. Develop and enhance campus mental health standards, programming, and education. | Improve access to mental health services on campus (through outreach, programming, and education to assure the retention, progression, and graduation of students). Combined with Goal 3, Obj. 1, Action Item 1 - Enhance the range of student academic and counseling support services, and widen access to them for all students | How? | Ensure the campus has an adequate number of qualified mental health providers and appropriate facilities to implement a comprehensive mental health program that allows for early prevention, intervention, and treatment of students with mental health conditions including: Stress, Anxiety, Depression, Trauma and post traumatic reaction, Sleep disruption, High risk alcohol, Abuse of substances, Difficulty with interpersonal relationships, Quick assessment of students who present in crisis |  | High Priority
|  |  | Who? | VPSA, Student Health, Counseling Services
|  |  | When? | Immediately
|  |  | Resources needed: | Reallocate funds; staffing funds for mental health outreach educators and others as determined; appropriate facilities with better access and confidentiality
Objective 3: Meet the health, nutrition, physical environment, and safety needs of the campus community. | 2. Develop and enhance campus mental health standards, programming, and education. | Enhance campus wide health promotion and prevention services | How? | Assess our students' health status to enhance campus-wide health promotion and prevention services and implement the American College Health Association (ACHA) - National College Health Assessment (NCHA) for baseline data and then every three years after to assess effectiveness of strategies and new and emerging trends on: Alcohol, tobacco, and other drug use; Sexual health; Weight, nutrition, and exercise; Mental health; Personal safety and violence |  | Medium Priority
|  |  | Who? | Student Health, Counseling, Disability Services, Wellness Center
|  |  | When? | Fall 2018 and every 3 years
|  |  | Resources needed: | Perhaps additional funding for survey costs and promotion of the survey
Objective 3: Meet the health, nutrition, physical environment, and safety needs of the campus community. | 3. Promote Title IX awareness and safety-related policies and procedures. |  | How? | Conduct annual campus climate surveys |  | Medium Priority
|  |  | Who? | Title IX Office
|  |  | When? | Immediately
|  |  | Resources needed: | ?
Objective 3: Meet the health, nutrition, physical environment, and safety needs of the campus community. | 3. Promote Title IX awareness and safety-related policies and procedures. |  | How? | Conduct annual IX training with campus community including Keep U Safe program |  | High Priority
|  |  | Who? | Title IX Office
|  |  | When? | Immediately and ongoing
|  |  | Resources needed: | $0.00
Objective 3: Meet the health, nutrition, physical environment, and safety needs of the campus community. | 3. Promote Title IX awareness and safety-related policies and procedures. |  | How? | Work collaboratively with various offices and departments within the institution to promote awareness and reporting |  | Medium Priority
|  |  | Who? | Title IX Office, Campus Security
|  |  | When? | Immediately
|  |  | Resources needed: | Staff
Objective 3: Meet the health, nutrition, physical environment, and safety needs of the campus community. | 3. Promote Title IX awareness and safety-related policies and procedures. |  | How? | Ensure the integrity and continuity of the Title IX complaint and investigation process throughout the institution |  | High Priority
|  |  | Who? | Title IX Office, HR, VPSA, Student Health
|  |  | When? | Immediately
Resources needed:
Objective 3: Meet the health, nutrition, physical environment, and safety needs of the campus community. | 4. Enhance healthy food choices on campus. |  | How? | Hire consultant to review current practices and recommend future options |  | High Priority - Complete
|  |  | Who? | VPSA, SGA, RHA
|  |  | When? | In progress - December 2017
|  |  | Resources needed: | VPSA
NOTE: The prioritized strategies have an X in the respective cell. Yellow cells can be deleted as they were combined with another strategy.

## Goal 5
Goal 5: Foster and grow collaborative partnerships locally, regionally, nationally, and globally.
Objectives | Action Items | Notes | Focus Questions | Answers | Additional Info | Cross References | Priority
Objective 1: Orchestrate collaborative efforts with P-12 partners and other institutions of higher education. | 1. Evaluate [and review] current procedure for partnership tracking, development and renewal, and coordination of agreements. | Survey for chairs, program directors, and campus leaders would be ready to go when we are ready - depends if we are doing one big survey on a number of items or if we are separating out surveys [need to decide the survey method and create a subcommittee to create the survey - go through note and indicate survey items in a color] Needs to include promotion of these agreements for recruitment of new students. Develop intentional articulation agreements and intentionally market them - on our website, create program of study sheets, readable and easily accessible | How? | Determine existing P-12 agreements/partnerships (and note which are formal, official, agreements and which are formal, partnerships; on-going, overtime) across the university | Goal 5 List 1 |  | Medium Priority
|  |  |  | Articulation Agreements and Memoranda of Understanding/Agreement | Goal 5 List 2
|  |  | Who? | VPAA; VPFA; VPSA; VP-Advancement; Associate Vice President of Graduate, Online, Distance and Continuing Education; Athletics (Department Chairs, Program Directors?); Registrar; Faculty
|  |  | When? | Spring 2018, ASAP
Resources needed:
Objective 1: Orchestrate collaborative efforts with P-12 partners and other institutions of higher education. | 1. Evaluate [and review] current procedure for partnership tracking, development and renewal, and coordination of agreements. |  | How? | Establish a central housing of partnership agreements for transparency, easy access, and to facilitate strategic planning and development |  | Goal 5, Objective 1, Item 3, Section 3 Goal 5, Objective 1, Item 4, Section 3 Goal 5, Objective 2, Item 1, Section 2 Goal 5, Objective 2, Item 2, Section 3 Goal 5, Objective 2, Item 3, Section 4 | Medium Priority
|  |  |  | Charge someone or a committee [out of the VPAA's office] a charge to oversee the articulation and MOU/A process, determine the students success of these programs, and determine new areas of growth. Assess the agreements to determine if we need to revise or eliminate any agreements that do not bring us students. (now!) |  | Goal 5, Objective 1, Item 3, Sections 1-3 Goal 5 Objective 1, Item 4, Section 3
|  |  |  | This group could also discuss the transferability for new students or a new group may need to be created to discuss transferability (it could fall under objective three); includes accepting credits, rotation schedule of course offerings, etc. |  | "could fall under objective three"
Designee to follow up with chairs, etc. on value of experience partnership
|  |  | Who? | VPAA; VPFA; VPSA; VP-Advancement; Associate President of Graduate, Online, Distance and Continuing Education; Athletics
|  |  | When? | Spring 2018 and ongoing
Resources needed:
Objective 1: Orchestrate collaborative efforts with P-12 partners and other institutions of higher education. | 2. Review all existing partnership agreements. | This is not complete. This is done at a macro level but still needs input from faculty & program director. | How? | Centralize |  |  | Medium Priority
Who?
|  |  | When? | Ongoing
Resources needed:
Objective 1: Orchestrate collaborative efforts with P-12 partners and other institutions of higher education. | 3. Develop strategic direction for current and future P-12 partnerships and higher education partnerships. | We must intentionally think about ways we are communicating this to the community | How? | Prioritize agreements as to needs/benefits/costs to the university according to an established rubric (like the one used in prioritization) [Great Western consortium] |  |  | High Priority
|  |  | Who? | the person/committee charged in 1d in conjunction with VPAA appointee |  | Goal 5, Objective 1, Item 1, Section 2
VPAA; VPFA; VPSA; VP-Advancement; Associate Vice President of Graduate, Online, Distance and Continuing Education; Athletic Director with faculty and staff participation from areas under study
|  |  | When? | Fall 2018
Resources needed:
Objective 1: Orchestrate collaborative efforts with P-12 partners and other institutions of higher education. | 3. Develop strategic direction for current and future P-12 partnerships and higher education partnerships. |  | How? | Renew, develop, combine, or re-imagine agreements with P-12 and higher education partnerships to provide excellent opportunities for our students, to enhance institutional growth, and to enhance institutional reputation |  |  | High Priority
|  |  | Who? | The person charged in 1d |  | Goal 5, Objective 1, Item 1, Section 2
VPAA; VPFA; VPSA; VP-Advancement; Associate Vice President of Graduate, Online, Distance and Continuing Education; Athletic Director with faculty and staff participation from areas under study
|  |  | When? | 2018-2019 SY and ongoing
Resources needed:
Objective 1: Orchestrate collaborative efforts with P-12 partners and other institutions of higher education. | 3. Develop strategic direction for current and future P-12 partnerships and higher education partnerships. |  | How? | Coordinate and house the agreements in centralized location as established in 1d |  | Goal 5, Objective 1, Item 1, Section 2 | High Priority
|  |  | Who? | The person charged in 1d and Agreement Facilitators |  | Goal 5, Objective 1, Item 1, Section 2
|  |  | When? | ongoing
Resources needed:
Objective 1: Orchestrate collaborative efforts with P-12 partners and other institutions of higher education. | 4. Enhance collaboration among NDUS and P-12 institutions. | Should we consider this more regionally, nationally and globally in a strategic manner? | How? | Opportunities for 2+2 programs | Goal 5 List 3 | Goal 2, Objective 1, Item 5, Section 3 | High Priority
Establish formal partnership with Williston State College
Explore outreach office/classroom in NW North Dakota - we need to be intentional about this position does and offers (Williston State College; Watford City High School/Rec Center)
Who?
When?
Resources needed:
Objective 1: Orchestrate collaborative efforts with P-12 partners and other institutions of higher education. | 4. Enhance collaboration among NDUS institutions. |  | How? | Renew, develop, combine, or re-imagine collaboration and agreements with NDUS partners to provide excellent opportunities for our students, to enhance institutional growth, and to enhance institutional reputation. |  |  | High Priority
|  |  | Who? | VPAA; VPFA; VPSA; VP-Advancement; Associate Vice President of Graduate, Online, Distance and Continuing Education; Athletic Director with faculty and staff participation from areas under study
|  |  | When? | 2018-2019 SY and ongoing
Resources needed:
Objective 1: Orchestrate collaborative efforts with P-12 partners and other institutions of higher education. | 4. Enhance collaboration among NDUS institutions. | Following the strategic director & cost-benefit analysis, which would include all items on p. 2 | How? | Coordinate and house the agreements in centralized location as established in 1d |  | Goal 5, Objective 1, Item 1, Section 2 | High Priority
|  |  | Who? | The person charged in 1d and Agreement Facilitators |  | Goal 5, Objective 1, Item 1, Section 2
|  |  | When? | ongoing
Resources needed:
Objective 2: Cultivate and maintain mutually beneficial relationships with local, regional, national, global communities, organizations, and partners. | 1. Review all partnerships. | One time projects - fit with community outreach (i.e. Media Literary Project) | How? | Determine existing partnership agreements across the university and where they are housed using a survey (NDCPD, Communication Disorders Clinic, Minot Head Start) |  |  | Medium Priority survey
|  |  | Who? | VPAA; VPSA; VP-Advancement; Associate Vice President of Graduate, Online, Distance and Continuing Education; Athletics (Department Chairs, Program Directors?)
|  |  | When? | Spring 2018
Resources needed:
Objective 2: Cultivate and maintain mutually beneficial relationships with local, regional, national, global communities, organizations, and partners. | 1. Review all partnerships. |  | How? | House the agreements in centralized location as established in 1C (1D?) |  | Goal 5, Objective 1, Item 1, Section 2 | Medium Priority
|  |  | Who? | VPAA; VPSA; VP-Advancement; Associate Vice President of Graduate, Online, Distance and Continuing Education; Athletics (Department Chairs, Program Directors?)
Change someone to […]
|  |  | When? | Spring 2018
Resources needed:
Objective 2: Cultivate and maintain mutually beneficial relationships with local, regional, national, global communities, organizations, and partners. | 1. Review all partnerships. |  | How? | Review all partnership agreements |  |  | Medium Priority
|  |  | Who? | VPAA; VPFA; VPSA; VP-Advancement; Associate Vice President of Graduate, Online, Distance and Continuing Education; Athletic Director (Department Chairs, Program Directors?)
|  |  | When? | Summer 2018
Resources needed:
Objective 2: Cultivate and maintain mutually beneficial relationships with local, regional, national, global communities, organizations, and partners. | 2. Develop strategic direction for current and future local, regional, national, and global partnerships with industries. |  | How? | Prioritize agreements as to needs/benefits/costs to the university according to an established rubric (like one used in prioritization) |  |  | Medium Priority
Intentionally look at […] and prioritize as to needs, benefits, and costs to the university
|  |  | Who? | VPAA; VPFA; VPSA; VP-Advancement; Associate Vice President of Graduate, Online, Distance and Continuing Education; Athletic Director with faculty and staff participation from areas under study
|  |  | When? | Fall 2018
Resources needed:
Objective 2: Cultivate and maintain mutually beneficial relationships with local, regional, national, global communities, organizations, and partners. | 2. Develop strategic direction for current and future local, regional, national, and global partnerships with industries. |  | How? | Renew, develop, combine, or re-imagine agreements with local, regional, national, and global industries to provide excellent opportunities for our students, to enhance institutional growth, and to enhance institutional reputation. |  |  | Medium Priority
|  |  | Who? | VPAA; VPFA; VPSA; VP-Advancement; Associate Vice President of Graduate, Online, Distance and Continuing Education; Athletic Director with faculty and staff participation from areas under study
|  |  | When? | 2018-2019 SY and ongoing
Resources needed:
Objective 2: Cultivate and maintain mutually beneficial relationships with local, regional, national, global communities, organizations, and partners. | 2. Develop strategic direction for current and future local, regional, national, and global partnerships with industries. |  | How? | House the agreements in centralized location as established in 1C (1D?) |  | Goal 5, Objective 1, Item 1, Section 2 | Medium Priority
|  |  | Who? | Agreement Facilitators
|  |  | When? | ongoing
Resources needed:
Objective 2: Cultivate and maintain mutually beneficial relationships with local, regional, national, global communities, organizations, and partners. | 3. Enhance partnerships with MAFB. |  | How? | Determine existing agreements and partnerships (Department of Defense MOU; MAFB MOU) |  |  | Medium Priority
Who?
When?
Resources needed:
Objective 2: Cultivate and maintain mutually beneficial relationships with local, regional, national, global communities, organizations, and partners. | 3. Enhance partnerships with MAFB. |  | How? | Establish committee to enhance relationships and opportunities with MAFB | Goal 5 List 4 |  | Medium Priority
|  |  | Who? | VPAA; VPFA; VPSA; Associate Vice President of Graduate, Online, Distance and Continuing Education with faculty and staff participation from areas under study
|  |  | When? | 2018-2019 SY and ongoing
Resources needed:
Objective 2: Cultivate and maintain mutually beneficial relationships with local, regional, national, global communities, organizations, and partners. | 3. Enhance partnerships with MAFB. |  | How? | Renew, develop, combine, or re-imagine collaboration and agreements with MAFB to provide excellent opportunities for our students, to enhance institutional growth, and to enhance institutional reputation |  |  | Medium Priority
United States Air Force GEM; United States Air Force AU-ABC
|  |  | Who? | VPAA; VPFA; VPSA; Associate Vice President of Graduate, Online, Distance and Continuing Education with faculty and staff participation from areas under study
|  |  | When? | 2018-2019 SY and ongoing
Resources needed:
Objective 2: Cultivate and maintain mutually beneficial relationships with local, regional, national, global communities, organizations, and partners. | 3. Enhance partnerships with MAFB. | Priority 4, following strategic discretion & cost-benefit analysis; act on these […] @ […] options | How? | House the agreements in centralized location as established in 1C (1D?) |  | Goal 5, Objective 1, Item 1, Section 2 | Medium Priority
|  |  | Who? | Agreement Facilitators
|  |  | When? | ongoing
Resources needed:
Objective 3: Leverage the expertise of individuals, groups, and organizations within the community to enhance learning and to strengthen university operations. | 1. Enhance MSU alumni relationships to promote their sharing of professional experiences. | ***We feel this could likely be combined with goal 4 or 6 | How? | Implement 21st Century Workforce Development Campaign | Look at Goals 4 & 6 along with 5 for overlap | Goal 2, Objective 1, Item 2, Section 1 Goal 3, Objective 2, Item 1, Section 2 Goal 4, Objective 1, Item 1, Section 4 Goal 6, Objective 1, Item 2 | Determine best goal for this objective/ action item
Who?
When?
Resources needed:
Objective 3: Leverage the expertise of individuals, groups, and organizations within the community to enhance learning and to strengthen university operations. | 1. Enhance MSU alumni relationships to promote their sharing of professional experiences. |  | How? | Attract alumni to participate and sponsor experiential learning opportunities for Minot State University students
|  |  | Who? | MSU Foundation/Alumni, Career Services, CEL
|  |  | When? | ongoing
|  |  | Resources needed: | Time, marketing
Objective 3: Leverage the expertise of individuals, groups, and organizations within the community to enhance learning and to strengthen university operations. | 2. Extend relationships between MSU and the Minot community to encourage community individuals and groups to participate in academic activities. |  | How? | Strengthen current partnerships | Goal 5 List 5 |  | Low Priority
|  |  | Who? | University Communications
|  |  | When? | ongoing
Resources needed:
Objective 3: Leverage the expertise of individuals, groups, and organizations within the community to enhance learning and to strengthen university operations. | 2. Extend relationships between MSU and the Minot community to encourage community individuals and groups to participate in academic activities. |  | How? | Attract community members to participate and sponsor experiential learning opportunities for Minot State University students |  |  | Low Priority
|  |  | Who? | MSU Foundation/Alumni, Career Services, CEL
|  |  | When? | ongoing
Resources needed:
Objective 3: Leverage the expertise of individuals, groups, and organizations within the community to enhance learning and to strengthen university operations. | 2. Extend relationships between MSU and the Minot community to encourage community individuals and groups to participate in academic activities. |  | How? | Expand usage for community members in the MSU Air Supported Dome (Bubble) |  | Goal 4, Objective 1, Item 2 Goal 4, Objective 3, Item 1, Section 5 | Low Priority
|  |  | Who? | Athletics, University Communications
|  |  | When? | ongoing
Resources needed:
Objective 3: Leverage the expertise of individuals, groups, and organizations within the community to enhance learning and to strengthen university operations. | 2. Extend relationships between MSU and the Minot community to encourage community individuals and groups to participate in academic activities. |  | How? | Partner with downtown Minot Resiliency programming to explore partnerships which benefit both parties |  |  | Low Priority
Explore Main Street initiative
Explore MSU downtown presence
|  |  | Who? | SEA Director
|  |  | When? | ongoing
Resources needed:
Objective 3: Leverage the expertise of individuals, groups, and organizations within the community to enhance learning and to strengthen university operations. | 2. Extend relationships between MSU and the Minot community to encourage community individuals and groups to participate in academic activities. |  | How? | Explore modes of transportation for students that expand our footprint into the greater Minot community |  |  | Low Priority
Bike share
Shuttle
|  |  | Who? | SGA, Sustainability Committee (Bike Share)
|  |  | When? | ongoing
Resources needed:
Objective 3: Leverage the expertise of individuals, groups, and organizations within the community to enhance learning and to strengthen university operations. | 3. Establish a learning in retirement program. |  | How? | Explore a Living & Learning Community in Beaver Ridge |  |  | Low Priority
Who?
When?
Resources needed:
Objective 3: Leverage the expertise of individuals, groups, and organizations within the community to enhance learning and to strengthen university operations. | 3. Establish a learning in retirement program. |  | How? | Enhance marketing of educational opportunities for senior citizens (65+ waiver) |  |  | Low Priority
Who?
When?
Resources needed:
Note on B47: Original Text: "Review all existing partnership agreements."
Note on B60: e: Original text: Develop strategic direction for current and future local, regional, national, and global partnerships with industries and other organizations.

## Goal 5 Lists
Goal 5 Lists
List 1: Existing P-12 Agreements/Partnerships | List 2: Articulation Agreements and Memoranda of Understanding/Agreement |  | List 3: Opportunities for 2+2 Programs | List 4: Relationships/Opportunities with MAFB | List 5: Current Community Partnerships
Mid-Dakota Educational Cooperative | MSU and DCB Memorandum of Understanding | renew 2022 | University of North Dakota partnership in online education | MAFB Chaplain Corps Suicide Intervention Training | Minot Symphony
Great Northwest Education Cooperative | Includes bachelor degree plans for: |  | Dakota College at Bottineau | International Military Ball | Western Plains Opera
Minot Public Schools | Early Childhood Education |  | Bismarck State College - various programs | MAFB Prairie Warrior Auction | MSU College for Kids
Bishop Ryan Catholic School | Physical Education |  | North Dakota State University | MAFB Violence Prevention team | MSU Athletic Camps
Souris Valley Special Services | Social Science Education |  | Social Work | MSU Military Appreciation events | Communication Disorders Clinic
Dual credit/Early Entry Students | Elementary Education Grades K-6 |  | Tentative: additional program in educational leadership | Military Day at the ND State Fair | VITA program
Headstart partnership | Elementary Education Grades 1-6 |  | Lake Region: Deaf Education | MAFB Backpack Brigade | Reading Clinic
Area preschool connections | Corporate Fitness |  | DSU: Social Work | MAFB Education Center | Preschool in Teacher Education
Student teaching | Athletic Training |  | Bakken U | MAFB Senior NCO membership
Job Corp | MSU and DCB Nursing Articulation Agreement | renew 2020
NDHSAA - Class A and B | MSU and DSU Master of Education MOU | renew 2021
Speech/Drama | MSU and LRSC Nursing Articulation Agreement | renew 2020
Music: Region 8/NW Music Festival/Jazz Festival/Middle School Band Festival | MSU and LRSC Peace Officer Training MOU | review each spring
Tech Day (one day, ongoing) | MSU and LRSC Sign Language Studies Articulation Agreement | renew annually - 2017-2018
Darwin Day (one day, ongoing) | MSU and MAFB MOU | renew annually - 2018
Marketplace for Kids (one day, ongoing) | MSU and MSU Foundation MOU | renew 2019
$MRTZ (one day, ongoing) | MSU and NDSCS Nursing Articulation Agreement | renew 2020
Spelling Bee (one day, ongoing) | MSU and NDSU Social Work MOA | renew annually - 2017-2018
Math Counts (one day, ongoing) | MSU and Three Affiliated Tribes Head Start MOU | renew annually - 2018-2019
| MSU and Trinity Health Agreement - Nursing for the Future | 2016 - 2021
| MSU and TMCC and DCB Criminal Justice MOU | renew 2016
Marketing - Students | MSU and WSC Nursing Articulation Agreement | renew 2020 or 2021
Marketing - Community Image | MSU and WSC Social Work Articulation Agreement | renew 2020
| MSU at BSC Memorandum of Understanding for 2017-2018 | review annually
| Statewide Early Childhood Articulation Agreement | renew 2021
| Statewide Nursing Articulation Agreement | renew 2018
| Northern Information Technology Consortium | review annually, signed 2017
California Community College Transfer Summary
Minnesota System of Colleges and Universities Transfer Summary
Montana University System Transfer Summary
Oregon Transfer Summary
South Dakota University System Transfer Summary
Washington State Community and Technical College Transfer Summary
Briercrest College and Seminary. Dual degree memoranda of agreement:
| Bachelor of Science, Addiction Studies | renew 2017
| Bachelor of Science, Communication Disorders | renew 2017
| Bachelor of Science, Social Work | renew 2017
| Bachelor of Science, Education | renew 2017
Lethbridge College. Dual degree memorandum of understanding:
| Bachelor of Science, Business Information Technology | renew 2017
Denmark - Aalborg University
| General MOU | renew 2018
| Student exchange addendum | renew 2018
Japan
| Japan College of Foreign Languages Transfer Articulation agreement | renew 2015
Norway - Arctic University of Norway - Harstad campus
| General MOU | renew every 5 years 2016
| Student exchange addendum | renew every 5 years 2016
| Social Work: field experience addendum | renew every 5 years 2016
Norway - University College of Southeast Norway - Bø campus
| General MOU | renew every 5 years 2018
| Student exchange addendum | renew every 5 years 2018
Poland - University of Lodz
| General MOU | renew every year 2017-2018
| Graduate certificate in Management Concepts | renew every year 2017-2018
Poland - SWPS University of Social Sciences and Humanities
| General MOU | renew 2020
Sweden - Kristianstad University
| General MOU | renew every 5 years 2018
| Student exchange addendum | renew every 5 years 2018
Taiwan - MingDao University
| MSU and MingDao University MOU | renew 2022

## Goal 6
Goal 6: Promote and recognize commitment to community engagement.
Objectives | Action Items | Focus Questions | Answers | Cross References | Priority
Objective 1: Build vibrant university and community relationships through meaningful engagement projects. [Change volungeer and service to engagement.] | 1. Establish campus-wide engagement coordination. (to bring groups to campus and go out to businesses to build relationships with community orgranizations - Lunch and learns) | How? | Hire a full-time outreach coordinator who will build external relationships with community businesses and partnerships for meaningful student engagement and internship opportunites or reimagine a position to be a PR coordinator for outreach and university relations. | Goal 6, Objective 1, Item 2 | High Priority - Complete after Survey
We must centralize internships to avoid having the responsibility fall entirely on faculty who may not have the established community relationships necessary for the best student placements
Who?
When?
|  | Resources needed: | New, free-standing position or repurpose a current position
Objective 1: Build vibrant university and community relationships through meaningful engagement projects. | 2. Increase alumni and off-campus organization sponsorship of student engagement projects. | How? | The 21st Century Workforce Development Campaign is a step toward this, but the program needs a dedicated employee to focus on building these relationships | Goal 2, Objective 1, Item 2, Section 1 Goal 3, Objective 2, Item 1, Section 2 Goal 4, Objective 1, Item 1, Section 4 Goal 5, Objective 3, Item 1, Section 1 | See Goal 5
|  | Who? | VPSA and Career Services
|  | When? | In progress
|  | Resources needed: | see Action Item 1.1 for full-time outreach coordinator and student placements | Goal 6, Objective 1, Item 1
Objective 1: Build vibrant university and community relationships through meaningful service and volunteer projects. | 3. Incorporate additional service and volunteer opportunities into existing courses and campus activities. | How? | First survey department/division chairs, coordinators, and student clubs to determine the current engagement projects that are occurring in classes and student clubs. (do first) |  | Medium Priority - Complete after Survey
Create a tiered engagement opportunity for each program of study and athletic group for students to work on throughout their college career and build leadership and mentoring opportunities within respective areas (e.g. the KMSU auction) (low priority)
Encourage (don't ignore) each department/degree to include an engagement project with freshman to seniors. Build in engagement projects. (high priority)
Do a better job of communicating the opportunities across campus to include more students, staff, and faculty (medium priority)
Create a once a month opportunity (low priority)
Use these engagement opportunities as resume builders to enhance the meaning of the experience
Encourage the use of Engagement Honor Roll to document activities
Use the mentorship within the engagement opportunity as moments for students to learn from each other and connect the dots between education and service and community
Move away from mandatory service projects that use students as free labor; make activity more meaningful (high priority)
Bridge the gap between academics and athletics in areas of engagement by streamlining the engageemnt project so that students see the benefits of service instead of the demands of hours of volunteering in many disconnected areas (high priority)
Create on-campus engagement projects during Welcome Week to create Minot State University as a destination
Move away from the word "volunteer" toward "engagement"
Allow more opportunities for students to decide where and how they donate their time and energy
|  | Who? | CETL
|  | When? | ASAP
|  | Resources needed: | Adjust faculty load as necessary to ensure program support and growth; possible release time for a faculty member to lead these efforts
Objective 2: Engage the community by offering and hosting activities and events in athletics, performing arts, culture, and academics. | 1. Promote proper community use of MSU facilities, especially during down time. | How? | President to work with the state to allow Minot State to compete with private sector for meeting and event space | Goal 4 | High Priority
|  |  | Evaluate how and how often facilities across campus are being used | Goal 4
There are events happening across campus regularly: Powwow, Futurepalooza, NOTSTOCK, music festivals, speech competitions, Marketplace for Kids, College for Kids, Science Olympiad, Summer Theatre, Class B tournaments, Special Olympics, Tech Day, Minot Symphony Orchestra, Western Plains Opera
Create a facilities budget for outside events on campus detached from athletics or department/academic area
Determine funding model for custodial and security during events on campus
Work with Sodexo on the food contract so that Minot State can be competitive in its options of food service for events
Extend coffee offerings (smoothies and fresh juices) and hours to make Minot State a destination prior to and following events on campus (e.g. people can grab a coffee/drink and sit and visit before attending the symphony, concert, or a play)
Extend bookstore hours before sporting events to encourage sales of Minot State gear
Discuss branding with the bookstore to collaborate with Athletics
Utilize the amphitheatre and Bubble for events and activities
Seek out concert events for the Dome and Ann Nicole Nelson Hall
|  | Who? | President
|  | When? | ??
|  | Resources needed: | Hire a facilities manager/event planner to schedule and coordinate events on campus - one person/office for all areas of campus; New free-standing position; Create an event approval process to prevent conflicts and work to cross-promote events on the same day; use common event schedule and room schedule/software | See objective 1.1 for short-term solution to grow a department
Objective 2: Engage the community by offering and hosting activities and events in athletics, performing arts, culture, and academics. | 2. Promote MSU at community events on campus. | How? | Cross-promote campus events at events on campus |  | Medium Priority
Utilize video boards and half-time announcements to highlight campus events in the coming week
Utilize advertisement space in programs (e.g. the sports schedule appears in the symphony program)
Market academic programs at appropriate events (e.g. sign, banner, program sheets)
|  | Who? | Marketing and University Communications, Publications and Design, Athletics, Theater, NW Arts Center, Music, etc.
|  | When? | Start now! Easy to do.
Resources needed:
Objective 2: Engage the community by offering and hosting activities and events in athletics, performing arts, culture, and academics. | 3. Expand successful discipline- or program-specific events to wider audience. | How? | Assess what we do well and prioritize |  | Medium Priority
What could be done to make those events better? e.g. KMSU Auction recruit MiSU celebrities to answer phones, invite packate donors to come on air and pitch the package they donated, bring in donors to talk about business on air, use teases to get people to stay tuned)
Assess where/whether there is room to grow events
Continue to update equipment and facilities to sell Minot State to prospective student while they are visiting
Better coordination between enrollment services, academic departments, and athletics to personalize the group visit to campus (e.g. connect prospective students with area while they are on campus for music festivals, NOTSTOCK, Futurepalooza); engagement coordinator visits with relevant groups on campus (e.g., chairs) to enhance current practices
|  | Who? | Engagement coordinator; facilities; SPBC (??)
|  | When? | Begin In 2018-2019
|  | Resources needed: | Engagement coordinator
Objective 3: Acknowledge the service achievements of the campus community. | 1. Enhance sharing of information about service achievements of the campus community through Public Information. "Look what the univeristy does for you!" | How? | Develop a method of tracking engagement hours for students, staff, and faculty (we have the engagement honor roll for students) |  | On-going
Develop a strategy for targeting outside media to cover engagement experiences to maximize exposure but not overwhelm media (out-reach coordinator to work with PIO)
Create a speaker's bureau to distribute information to community agencies
|  | Who? | University Communications and Department/Division Chairs and Directors; CETL
|  | When? | Begin In 2018-2019
|  | Resources needed: | On-going
Objective 3: Acknowledge the service achievements of the campus community. | 2. Develop innovative ways to recognize service achievements of students, staff, and faculty through external agencies. | How? | High five award is being used now through Staff Senate as a creative way to recognize staff; Faculty Senate should adopt a similar program for faculty | Move to Goal 2 - High Five Award for faculty or something like it. | On-going
Highlight a volunteer of the month: student, faculty, staff, organization
|  | Who? | University Communications
|  | When? | 2018-2019
|  | Resources needed: | Nomination process
Note on B3: e: Original text: Establish campus-wide internship coordination.
Note on B28: Miller, Emily: Original text: Promote community use of MSU facilities.
Note on B50: e: Goal 4 document says "START HERE"